Project Plan Document

CareConnect Team D

University of Maryland Global Campus

Software Engineering 670 9040 Software Engineering Capstone

Dr. Mir Assadullah

June 13th, 2026

Version 2.0

Contributors:

Angel Guanlao, Bernabe Garcia, Cristobal Garcia, Davon Davis, Nhial Mayar

# Revision History

Table Revision History

| Team Name | Date | Reason for Changes | Version |
| --- | --- | --- | --- |
| Team D | 05/30/2026 | Initial document submission | 1.0 |
| Team D | 06/13/2026 | Revisions based on 1.0 feedback | 2.0 |

# Table of Contents

Revision History	3

Table of Contents	4

1. Executive Summary	8

1.2 Purpose	8

1.3 Scope	8

2. Objectives and Goals	9

2.1 Goals	9

2.2 Objectives	9

3. Scope of Work	10

3.1 In-Scope	10

3.1.1. Electronic Visit Verification (EVV) Enhancements	10

3.1.2. AI-Assisted Invoicing - Migration to AWS Bedrock with Claude	10

3.1.3. QR Code and Link Invite Care Circle Onboarding	11

3.1.4. Wearable Device Integration	11

3.1.5. Home Care Document Digitization	12

3.1.6. Screening and Initial Assessment	12

3.1.7. Comprehensive Assessment	13

3.1.8. Live EVV Aggregator Submission	13

3.2 Out-of-Scope	13

3.2.1. Production Healthcare Billing Integration	13

3.2.2. Electronic Health Record and FHIR Integration	14

3.2.3. Custom Hardware or Medical Device Development	14

3.2.4. Clinical Diagnosis by AI	14

3.2.5. Multilingual Support	14

3.2.6. Legally Binding E-Signatures	14

3.2.7. Machine Learning Model Development	14

3.2.8. Accessibility Certification	14

3.2.9. Deployment, Infrastructure, and RBAC Configuration	14

3.2.10. USPS Informed Delivery and AI Call Summaries	14

4. Stakeholders	16

4.1 Internal	16

4.2 External	16

5. Timeline & Milestone	17

5.1 Timeline and Milestone Table	17

5.2 Planning Approach	17

5.3 Gantt Chart	18

6. Technical Architecture	19

6.1 Architectural Objectives	19

6.2 Logical System Architecture	19

6.3 High-Level System Architecture Diagram	21

6.4 Architectural Rationale	21

6.5 Technology Stack Summary	22

6.6 Security	23

6.6.1 Data Protection	23

6.6.2 Authentication and Access Control	23

6.6.3 APIs and Infrastructure	24

6.6.4 Monitoring and Compliance	24

7. Project Deliverables	26

8. Risk & Mitigation	27

8.1 Risk Probability Matrix	27

8.2 Risk Identification, Probability, and Mitigation	27

8.3 Risk and Budget Alignment	29

9. Budget Estimate	30

9.1 Labor Cost Estimate	30

9.2 Budget Summary by Role	34

9.3 Infrastructure Cost	34

9.3.1 Core Services	34

9.4 Total Budget Summary	35

9.5 EVM Tracking Table	35

10. Roles & Responsibilities	37

10.1 Roles	37

10.2 RACI Matrix	37

11. Monitoring and Reporting	39

11.1 Objectives	39

11.2 Intra-Team Monitoring and Reporting	39

11.3 Project Communications	39

11.3.1 Internal Meetings	39

11.3.2 Internal-External Meetings	39

11.3.3 Cross-Team Meetings	39

11.4 Quality Plan	40

12. Assumptions	41

13. Constraints	42

14. Work Breakdown Structure (WBS)	43

14.2 WBS Hierarchy	49

15. Change Management Procedures	50

15.1 Initiation	50

15.2 Review	51

15.3 Authorization and Implementation	51

15.4 Version Control and Traceability	51

15.5 Emergency or Critical Changes	52

16. Appendices	53

16.1 Glossary of Terms	53

16.2 References	57

# 1. Executive Summary

The CareConnect Team D project focuses on enhancing and extending the existing CareConnect healthcare platform through improvements to Electronic Visit Verification (EVV), AI-assisted invoicing, wearable device integration, QR/link invitation workflows, and home care document digitization. The project supports caregivers, patients, and care-circle members by improving healthcare coordination, onboarding workflows, assessment documentation, and operational efficiency.

This Project Management Plan (PMP) defines the project objectives, deliverables, timeline, responsibilities, and operational procedures for Team D’s assigned feature set. The document serves as a guide for project execution, communication, monitoring, and change management throughout the SWEN 670 Capstone lifecycle.

## 1.2 Purpose

The purpose of this project is to design, develop, and document enhancements for the CareConnect platform that improve healthcare workflow efficiency, patient onboarding, assessment digitization, and caregiver coordination. Team D will focus specifically on extending EVV capabilities, integrating AI-assisted invoicing workflows using AWS Bedrock/Claude, supporting wearable device data collection, and digitizing home care intake and assessment documentation.

## 1.3 Scope

This project includes analysis, design, implementation, and testing for the following major feature areas:

- EVV feature enhancements and aggregator dependency tracking

- AI-assisted invoicing workflow improvements using AWS Bedrock/Claude

- QR code and invite-link onboarding workflows

- Wearable device integration feasibility and implementation

- Home care document digitization

- Screening and assessment workflow support

Out-of-scope items include large-scale production healthcare integrations, custom hardware development, and advanced enterprise reporting beyond the scope of the academic MVP timeline.

# 2. Objectives and Goals

## 2.1 Goals

The following goals define the high-level outcomes Team D aims to achieve through the CareConnect capstone project. These goals guide prioritization decisions, scope of boundaries, and team alignment throughout the development lifecycle.

- Deliver secure and user-friendly healthcare workflow enhancements within the CareConnect platform.

- Improve caregiver efficiency through digitized workflows and automation.

- Enhance onboarding and collaboration within patient care circles.

- Support scalable and maintainable healthcare data collection and management.

- Deliver all assigned features and documentation within the SWEN 670 capstone schedule.

- Follow Agile-Scrum development practices with iterative sprint-based delivery.

## 2.2 Objectives

- Review and improve the existing EVV workflow and identify required enhancements.

- Support aggregator dependency tracking and integration readiness.

- Implement or prototype AI-assisted invoice processing using AWS Bedrock and Claude.

- Develop QR code and secure invite-link workflows for care-circle onboarding.

- Research and integrate wearable health data where feasible.

- Digitize selected home care service forms and assessments.

- Create structured workflows for screening and comprehensive assessments.

- Maintain updated technical documentation, testing status, and deployment readiness throughout development.

# 3. Scope of Work

Team D is responsible for seven feature areas within the CareConnect healthcare coordination platform. Some of these areas extend functionality that was partially developed by prior capstone cohorts, and others represent entirely new capabilities with no existing implementation. This section defines what Team D will deliver, what falls outside the team’s responsibilities, and the reasoning behind those boundaries. All work is scoped to support the Minimum Viable Product within the academic timeline while laying a maintainable foundation for future development.

## 3.1 In-Scope

### 3.1.1. Electronic Visit Verification (EVV) Enhancements

Electronic Visit Verification is a federally mandated system that requires home care agencies to electronically record when and where caregivers begin and end each patient visit. The Spring 2026 cohort delivered a functional EVV module that supports visit scheduling, location-based check-in and check-out, mid-visit documentation, offline queuing, and export of visit records in EDI formation for submission to payers.

Team D’s responsibility in this area focus on reviewing the existing implementation to identify gaps, delivering any outstanding enhancements identified by the client, and tracking the integration with the external aggregator system responsible for routing visit records to state Medicaid programs. Specific deliverables include:

- A documented review of the current EVV workflow, data fields, and system endpoints, identifying what is complete and what requires further work.

- Implementation of any new EVV features identified during the gap review or directed by the client.

- A dependency tracking record for the EVV aggregator, including current status, responsible party, and blocking conditions, surfaced on the administrative dashboard.

- Written documentation of the integration design for programmatic aggregator submission, including data field mapping and error handling.

### 3.1.2. AI-Assisted Invoicing - Migration to AWS Bedrock with Claude

CareConnect includes an Invoice and Billing Assistance that allows caregivers to upload photographs or scans of medical bills. The system automatically extracts key information from those documents such as vendor name, date, invoice number, individual line items, and totals, using artificial intelligence. A reviewer then confirms or corrects the extracted data before the invoice is saved. This workflow was delivered by the Spring 2026 cohort.

The current implementation uses an AI service called DeepSeek. Team D is responsible for migrating this invoice extraction capability to Amazon Web Services Bedrock using Anthropic’s Claude model. This change updates the underlying AI provider while preserving the full reviewer experience that users already depend on. Specific deliverables include:

- A review of the existing invoice extraction service to understand the current DeepSeek integration and define what much change for Bedrock and Claude compatibility.

- A review of the existing invoice extraction service to understand the current DeepSeek integration and define what much change for Bedrock and Claude compatibility.

- Implementation of the migration from DeepSeek to Claude via AWS Bedrock, using the platform’s existing credential management infrastructure.

- Validation that Claude produces invoice extractions of comparable or greater accuracy than DeepSeek, tested against a representative set of invoice documents.

- Confirmation that all existing reviewer capabilities (field correction, duplicate flagging, approval workflow, and audit logging) remain fully functional after the migration.

- Technical documentation of the Bedrock model configuration, region, and any prompt design decisions required to support Claude’s response format.

### 3.1.3. QR Code and Link Invite Care Circle Onboarding

CareConnect organizes users into care circles - groups that connect a patient with their caregivers and authorized family members. A basic mechanism for inviting users into these groups via QR code and email link exists in the current platform. Team D is responsible for formalizing this into a secure, reliable onboarding flow that gives invited users clear context about who is inviting them and what they are joining, and that handles edge cases such as expired or already-used invitations gracefully. Specific deliverables include:

- A review of the existing invite and patient-linking mechanisms to establish what is already working and what must be built or improved.

- A token-based invitation system that generates a unique, time-limited code for each care circle invitation.

- Delivery of that invitation code via both a shareable URL link and a scannable QR code.

- A confirmation screen that displays the inviting user’s identity and the name of the care circle before the recipient accepts.

- Appropriate handling of expired, already-used, and invalid tokens, with clear messaging for the recipient.

- Automatic assignment of the correct care-circle membership and user role upon successful invitation acceptance.

- Documentation of the invitation lifecycle, including token expiration rules and what happens at each step of the flow.

### 3.1.4. Wearable Device Integration

CareConnect is designed to receive health data from wearable devices such as fitness trackers and smartwatches, giving caregivers a more complete picture of a patient’s day-to-day health. The architectural groundwork for this integration exists in the current codebase, but the connections to device platforms (Fitbit, Apple Health, and Google Health Connect) have not been fully implemented. Team D is responsible for completing these integration and enabling the alert capabilities that make the data actionable. Specific deliverables include:

- Implementation of the authorization flows required to connect each supported device platform to a user’s CareConnect account, in compliance with each platform’s security requirements.

- Display of the most recently synced health metrics, including sync time and connection status, on the caregiver and patient dashboards.

- Configurable alert thresholds for each metric type, with caregiver notifications delivered through the platform’s existing real-time alert channel when a threshold is exceeded.

- A data log recording the source device, metric type, value, unit of measurement, and timestamp for each synced reading.

- User notification when a connected device has not reported new data within a defined period, indicating a possible sync failure.

- Documentation of which device platforms are fully implemented, which remain partially integrated, and any known limitations of the available APIs.

### 3.1.5. Home Care Document Digitization

Home care agencies rely on a set of standard forms to onboard and support employees and service recipients, including tax withholding forms, employment eligibility verification, direct deposit authorization, and health-related documentation. None of these forms currently exist in digital form within CareConnect. Team D is responsible for building structured digital versions of the highest-priority forms, enabling staff to complete, submit, and track these documents within the application rather than through paper processes. Specific deliverables include:

- A review of all client-provided home care forms, including the W-4, I-9, Direct Deposit Authorization, VA Sworn Disclosure Statement, Health Documents, General Hiring form, and Pre-Hire Forms to establish which will be digitized in the current milestone and which will be deferred.

- Structured digital intake forms for the highest-priority documents, with field-level validation that prevents incomplete submissions.

- Persistent storage of submitted form data, linked to the appropriate user profile.

- A status tracking system showing each document’s current state: draft, submitted, pending review, or accepted.

- An administrative review interface allowing authorized users to accept submitted documents or return them with a stated reason.

- Documentation of which forms were implemented, which were deferred, and the reasoning behind those decisions.

### 3.1.6. Screening and Initial Assessment

When an individual is referred for home care services, a clinician completes an initial screening to determine eligibility, understand the person’s immediate needs, and decide on next steps. No structured screening workflow currently exists in CareConnect. Team D is responsible for building a digital screening form that captures the fields required to support this clinical intake process. Specific deliverables include:

- A structured screening form capturing the reason for the service request; the individual’s disposition, such as referral, placement on a waiting list, or admission; whether the individual qualifies for admission; whether an Individual Support Plan should be initiated; and the individual’s primary diagnosis.

- Fields for presenting needs, including psychiatric needs and general support requirements, current medical problems, current medications, substance use history, and at-risk behavior toward self or others.

- The ability to save a screening record as a draft or submit it as complete.

- Association of each completed screening record with the patient profile, displaying the submission date and the identity of the assessor who completed it.

### 3.1.7. Comprehensive Assessment

Following the initial screening, a more detailed comprehensive assessment documents a patient’s full health, social, functional, and personal history. This assessment informs care planning and ongoing service delivery. No comprehensive workflow currently exists in CareConnect. Team D is responsible for building a structured digital form that captures the full breadth of information required for this clinical evaluation. Specific deliverables include:

- A structured assessment form capturing the onset and duration of the individual’s presenting problems; social, behavioral, development, and family history; cognitive functioning including identified strengths and limitations; and employment, vocational, and educational background.

- Fields for previous treatment history and outcomes, current financial resources and benefits, and ongoing medical care needs.

- Health history fields covering allergies, chronic conditions, communicable diseases, nutritional needs, physical activity restrictions, special supervision requirements, significant past illnesses and hospitalizations, and relevant family medical history.

- Functional status fields addressing fall risk, mobility and adaptive equipment needs, daily living skills, housing arrangements, transportation needs, and communication requirements.

- Legal status fields for relevant charges, convictions, probation, and parole status.

- Fields for mental health history, substance use history, and history of abuse, neglect, or trauma.

- The ability to save an assessment as a draft or submit it as complete, with all completed assessments retained in the patient record to support longitudinal review.

### 3.1.8. Live EVV Aggregator Submission

Programmatic, real-time submission of visit records to the state Medicaid aggregator is deferred. The aggregator is a third-party system that requires external account access and API credentials that have not yet been confirmed. Team D will deliver the integration design and track this as a formal project dependency, but live submission is not committed for the current milestone.

## 3.2 Out-of-Scope

### 3.2.1. Production Healthcare Billing Integration

Full integration with insurance payers, claims processing systems, or production billing platforms is outside the scope of this project. The invoicing feature is limited to AI-assisted document review within CareConnect and does not connect to external billing infrastructure.

### 3.2.2. Electronic Health Record and FHIR Integration

Integration with external Electronic Health Record systems or the HL7 FHIR healthcare data exchange standard is deferred. The technical complexity and external system coordination required for these integrations exceed what is achievable within the academic timeline.

### 3.2.3. Custom Hardware or Medical Device Development

No custom wearable hardware will be developed. Wearable integration is limited to health data accessible through the publicly available APIs of Fitbit, Apple HealthKit, and Google Health Connect.

### 3.2.4. Clinical Diagnosis by AI

The AI features within CareConnect are informational tools only. The system will not generate, suggest, or imply a clinical diagnosis under any circumstances. All AI-produced outputs must be reviewed by a human before any action is taken, and all AI responses must carry appropriate disclaimers consistent with existing platform policy.

### 3.2.5. Multilingual Support

Full multilingual support is deferred to a future release. The current MVP supports English only. Spanish language support and voice control localization are the responsibility of Team C and are not included in Team D’s scope.

### 3.2.6. Legally Binding E-Signatures

The digital forms implemented by Team D do not include legally enforceable electronic signatures. E-signature functionality requires legal and compliance review that falls outside the academic scope and is deferred to a future milestone.

### 3.2.7. Machine Learning Model Development

Training or fine-tuning AI models, building predictive health analytics, or developing intelligent assessment recommendation engines are outside Team D’s scope. These capabilities require substantial historical data, model validation infrastructure, and specialized expertise that are not available within the academic timeline.

### 3.2.8. Accessibility Certification

Formal accessibility certification and production of a Voluntary Product Accessibility Template are the responsibility of Team B. Team D will adhere to accessible development practices in all new features but will not independently certify compliance or produce a VPAT.

### 3.2.9. Deployment, Infrastructure, and RBAC Configuration

CI/CD pipeline management, production deployment, AWS environment configuration, Bedrock credential provisioning, and the core Role-Based Access Control framework are the responsibility of Team A. Team D applies the existing access control patterns to all new features but does not own or modify the underlying infrastructure.

### 3.2.10. USPS Informed Delivery and AI Call Summaries

USPS Informed Delivery integration and AI-generated call or visit summaries are assigned to Team E and are outside Team D’s scope.

# 4. Stakeholders

## 4.1 Internal

The following individuals and groups have a direct stake in the success of this project and are engaged throughout the project lifecycle in various capacities ranging from oversight and review to day-to-day collaboration.

- Client (Roy Gordon)

- Faculty/Mentor (Dr. Assadullah)

- Project Lead (Joriel Rivas)

- Technical Lead (Davon Davis)

- Developers, BA, QA, UI/UX

## 4.2 External

The following external stakeholders represent the individuals, organizations, and service providers who interact with or are affected by the CareConnect platform. While they operate outside the direct project team, their needs, dependencies, and expectations inform design decisions and scope boundaries throughout the development lifecycle.

- Caregivers – End users responsible for patient care coordination and workflow management.

- Patients/Home Care Recipients – Individuals receiving services through the CareConnect platform.

- Healthcare Organizations/Home Care Agencies – Organizations that may utilize EVV, assessment, and onboarding workflows.

- Third-Party Platform Providers – External providers such as AWS Bedrock, wearable APIs, and EVV aggregators.

- Future Integration Partners – Potential healthcare systems and external vendors supporting interoperability.

# 5. Timeline & Milestone

## 5.1 Timeline and Milestone Table

Table 5.1: Milestone and Timeline

| Milestone | Deliverables | Due Date |
| --- | --- | --- |
| Milestone 1 | Project Plan, SRS | 05/30/026 |
| Milestone 2 | Technical Design Document, Software Test Plan | 06/13/2026 |
| Milestone 3 | Programmer Guide, Deployment and Operations Guide, Software Test Plan | 07/25/2026 |
| Milestone 4 | User Guide, Test Report | 08/04/2026 |

## 5.2 Planning Approach

The following tools, methodologies, and practices form the operational backbone of Team D’s delivery approach. These methods support sprint-based progress tracking, collaborative development, and consistent documentation throughout the capstone timeline.

- Agile-Scrum methodology with weekly sprint planning and reviews.

- GitHub will be used for source control, pull requests, and issue tracking.

- Microsoft Teams and Slack will be used for team communication and meetings.

- Shared documentation repositories will be maintained for deliverables and requirements.

- Weekly progress tracking will be performed against sprint goals and milestone deadlines.

## 5.3 Gantt Chart

Figure 5.3: Gantt Chart of Project Milestones

# 6. Technical Architecture

This section documents the backend architecture decisions that support Team D's advanced CareConnect features, including AI-assisted invoicing, wearable integrations, real-time communications, document digitization, and external service coordination. The proposed architecture uses a scalable Spring Boot service foundation, a relational persistence model, and managed cloud integrations so the platform can support pilot-scale deployment while preserving security, maintainability, and operational visibility.

## 6.1 Architectural Objectives

Table 6.1: Architectural Objectives Table

| Objective | Rationale |
| --- | --- |
| Scalability | Support pilot growth and bursty workloads across REST APIs, WebSockets, AI calls, and media flows without requiring permanent overprovisioning. |
| Security and Data Protection | Protect healthcare-adjacent and socially sensitive data through layered authentication, RBAC, encrypted transport, controlled secrets management, and auditability. |
| Deployment Flexibility | Allow local containerized development while supporting low-operations cloud deployment patterns such as AWS Lambda and managed services. |
| Integration Readiness | Provide stable service boundaries for AWS services, wearable platforms, notification providers, email providers, Stripe, and identity federation. |
| Maintainability and Observability | Preserve a modular service design with environment-specific configuration, health checks, monitoring, backup discipline, and operational governance. |

Note. This table describes the key architectural objectives and their rationale.

## 6.2 Logical System Architecture

Table 6.2:  Logical System Architecture Table

| Tier | Logical Component | Responsibilities | Tech Choice |
| --- | --- | --- | --- |
| Client Layer | Web and mobile clients | Present dashboards, onboarding flows, wearable summaries, invoice review, document workflows, and assessment experiences. | HTTPS clients with WebSocket support |
| API and Security Layer | REST endpoints, auth filters, CORS policies, token validation | Accept client requests, enforce JWT and OAuth2 validation, apply RBAC, and protect cross-origin access. | Spring Boot + Spring Security + JWT/OAuth2 |
| Application Services Layer | Domain and workflow services | Execute business logic for AI brokering, messaging, notifications, analytics, documents, EVV support, and wearable workflows. | Spring Boot service modules |
| Persistence and Integration Layer | Repositories, relational persistence, outbound integration adapters | Store structured system data and broker calls to external services using controlled service interfaces. | Spring Data JPA + PostgreSQL |
| External Cloud and Third-Party Services | Cloud storage, AI, media, notification, email, billing, identity, and device services | Provide durable storage, inference, transcription, telehealth, push/email delivery, billing state, federated identity, and wearable data exchange. | AWS S3/Bedrock/Chime/Textract/Transcribe, Firebase, SendGrid, Stripe, Google OAuth, wearable APIs |

Note. This table describes the logical layers of the system architecture.

## 6.3 High-Level System Architecture Diagram

The following structural representation illustrates the data flow and system boundaries of the proposed CareConnect backend architecture:

Figure 6.3 High-Level System Architecture Diagram

Note. This diagram illustrates the system component relationships.

## 6.4 Architectural Rationale

Table 6.4:  Architectural Rationale Table

| Concern | Design Decision | Justification |
| --- | --- | --- |
| Deployment model | Retain Docker for local development and prefer managed/serverless AWS deployment for the pilot release. | This lowers developer setup friction while enabling elastic production execution with reduced infrastructure administration overhead. |
| Relational persistence | Use PostgreSQL as the authoritative system of record for users, patients, caregivers, vitals, documents, notifications, and billing-related entities. | The domain is highly relational and benefits from transactional consistency, indexing, and schema-governed storage. |
| Managed service integration | Use bounded adapters for S3, Bedrock, Chime, Textract, Transcribe, Firebase, email, Stripe, and identity providers. | Managed services accelerate delivery, reduce custom infrastructure burden, and align with the feature set already planned for Team D. |
| Security governance | Centralize secrets, enforce least privilege, and strengthen observability, backup, and access-review practices. | Because the platform handles sensitive healthcare-adjacent information, operational controls are as important as feature delivery. |

## 6.5 Technology Stack Summary

Table 6.5: Technology Stack Summary

| Layer | Technology | Purpose | Notes |
| --- | --- | --- | --- |
| Client Access | Web and mobile application clients | Provide user-facing workflows for onboarding, EVV visibility, documents, invoicing, and wearable monitoring. | Consume backend functionality over HTTPS and WebSocket channels. |
| Frontend | Flutter + Dart | Single frontend codebase for Web, iOS, Android, and desktop surfaces in the academic MVP timeline | Supports rapid feature expansion without splitting teams across separate web/mobile codebases |
| Backend | Java 17 + Spring Boot 3.4.5 | Host REST APIs, security controls, workflow orchestration, and service integrations. | Primary application framework for Team D backend capabilities. |
| Database | PostgreSQL + Spring Data JPA | Persist structured relational records and support reporting and operational workflows. | Well aligned to strongly related healthcare and coordination data. |
| Deployment | Docker + AWS Lambda / managed AWS services | Support local development and pilot production deployment. | Provides deployment flexibility without changing the core service model. |
| AI / Media / Cloud | AWS Bedrock, Chime SDK, S3, Textract, Transcribe | Enable inference, telehealth media, file storage, OCR, and transcription services. | Primary advanced capability stack for Team D features. |
| Third-Party Integration | Stripe, Firebase Cloud Messaging, SendGrid/Mailgun, Google OAuth, wearable APIs | Handle billing, push delivery, transactional email, federated identity, and external device connectivity. | External provider access should remain secret-managed and policy-governed. |

## 6.6 Security

### 6.6.1 Data Protection

The security strategy follows defense-in-depth with data minimization at the client boundary and encryption in transit and at rest.

Data protection controls for Team D workflows include:

- Encryption in transit: All client-to-backend traffic uses HTTPS with TLS 1.2+ (or higher) and certificate validation. No production workflow traffic is sent over plaintext channels.

- Encryption at rest: Sensitive backend data is encrypted at rest using managed cloud encryption controls. On-device sensitive artifacts (for example auth tokens) are stored in secure platform keystores through secure storage libraries, not plain local preferences.

- Data minimization: UI forms collect only fields required to execute EVV, invoicing, onboarding, wearable, and assessment workflows. Optional or derived data is excluded unless a downstream rule explicitly requires it.

- Sensitive data handling: Logs, analytics events, and client-side error payloads must avoid PHI/PII content where possible and use redaction for identifiers when troubleshooting is necessary.

- Retention and lifecycle: Temporary drafts and offline queue records are scoped to operational need, synchronized quickly, and purged according to retention policy to reduce residual exposure.

### 6.6.2 Authentication and Access Control

Authentication and authorization are implemented as layered controls across frontend route guards and backend policy enforcement.

AuthN/AuthZ approach:

- Authentication model: Token-based authentication (short-lived access token with refresh/session continuity strategy) is used for all protected application interactions.

- Authorization model: Role-based access control (RBAC) maps users to role claims (for example caregiver, patient/family, assessor, admin) and governs allowed dashboards, actions, and feature entry points.

- Least privilege: Users receive the minimum permissions needed for assigned tasks; feature-gated modules (such as invoice AI reviewer flows) are denied by default unless entitlement is present.

- Frontend enforcement: Route-level guards and view-level action constraints prevent accidental access to unauthorized pages or controls.

- Backend enforcement: APIs remain the policy authority and validate identity, role, and action scope on every protected request. Frontend checks improve UX but do not replace server authorization.

- Session security: Session timeout, token renewal controls, and explicit logout/revocation paths reduce unauthorized reuse risk.

### 6.6.3 APIs and Infrastructure

API and infrastructure protection is designed around managed entry points, segmented network boundaries, and controlled external integrations.

API gateway and network controls:

- API gateway protection: All frontend calls traverse managed API entry points that enforce authentication, request validation, throttling/rate limits, and standardized error handling.

- Web application firewall (WAF): WAF rules are applied at the public edge to reduce common web threats (for example injection and abusive traffic patterns) before requests reach application services.

- Network isolation: Application and data services are deployed in segmented network zones (for example private subnets and restricted security groups) to limit lateral movement and direct exposure.

- Secrets management: API keys, tokens, and integration credentials are managed through environment/secret stores; secrets are not hardcoded in client code or repository history.

- Integration abstraction: Wearables and invoice AI providers are consumed through backend adapters so provider changes do not expose secrets or force direct client coupling.

- CORS and endpoint governance: Only approved origins and required methods/headers are enabled for public APIs, minimizing cross-origin abuse and over-broad access.

### 6.6.4 Monitoring and Compliance

Monitoring and compliance readiness are maintained through auditable events, automated security checks, and milestone-based governance reviews.

Monitoring and compliance controls:

- Audit logging: Security-relevant and business-critical actions (login, invite issuance/acceptance, invoice approval, assessment submission, role-sensitive updates) are logged with actor, timestamp, action, and outcome metadata.

- Centralized observability: Application, API, and infrastructure logs/metrics are aggregated for alerting on anomalous activity, repeated auth failures, and service degradation.

- Vulnerability scanning: Dependency scanning, static analysis, and container/image scanning are performed in CI and before release; critical findings are tracked to remediation before production promotion.

- Security testing checkpoints: Release gates include API security checks, auth/authorization regression validation, and targeted penetration-style test scenarios for high-risk workflows.

- Compliance traceability: Requirements-to-control mapping and test evidence are maintained in project artifacts to support HIPAA-aligned handling expectations and capstone audit review.

- Incident readiness: Defined escalation paths and response playbooks guide triage, containment, communication, and post-incident corrective actions.

# 7. Project Deliverables

The following deliverables represent the complete set of artifacts Team D is committed to producing across all four milestones of the SWEN 670 capstone. Each deliverable serves a distinct purpose in documenting, implementing, or validating the team's assigned feature set, and together they constitute the working software and supporting documentation required for project completion.

- Project Plan - Defines the project scope, goals, stakeholders, timelines, and overall execution strategy.

- SRS - Documents EVV, invoicing, wearable integrations, QR workflows, and digitization requirements for the application.

- Technical Design Document - Provides architectural decisions, workflow diagrams, system design details, and implementation planning for assigned features.

- Software Test Plan - Defines the testing strategy, testing scope, test environments, and validation approach for system functionality and quality assurance.

- Programmer Guide - Provides technical guidance for future developers, including code structure, setup instructions, workflows, and development standards.

- Deployment and Operations Guide - Documents of deployment procedures, infrastructure configuration, environment setup, and operational maintenance processes.

- EVV Enhancement Features - Implements and documents updates to EVV workflows and related system functionality.

- QR/Invite Workflow - Implements secure onboarding and user-linking workflows using QR codes and invite links.

- Wearable Integration Research - Provides feasibility analysis, integration planning, and implementation of documentation for wearable device support.

- AI Invoice Workflow - Implements or prototypes of AI-powered invoice processing workflows using Bedrock/Claude integrations.

- Digitized Home Care Forms - Develops structured intake, assessment, and home care form workflows for digital completion and management.

- Testing Documentation - Includes test plans, test cases, execution results, defect tracking, and validation evidence for completed functionality.

- User & Technical Documentation - Includes README updates, user guidance, deployment instructions, and supporting technical documentation for final deliver

# 8. Risk & Mitigation

## 8.1 Risk Probability Matrix

The risk matrix below categorizes identified project risks by probability and impact. High-probability or high-impact risks are prioritized for active mitigation and tracked weekly in the team's sprint review.

Table 8.1:  Risk Probability and Impact Matrix

| Risk Level | Risk 1 | Risk 2 | Risk 3 | Risk 4 |
| --- | --- | --- | --- | --- |
| High Impact / High Probability | R-001 EVV aggregator access | R-002 Bedrock provisioning |  |  |
| High Impact / Low Probability | R-003 PHI/AI data leak | R-005 Token replay |  |  |
| Medium Impact / Medium Probability | R-004 Wearable API limits | R-006 Scope creep | R-007 Team availability | R-008 Merge conflicts |

Note. Risk probability and impact ratings are reviewed weekly and updated if conditions change.

## 8.2 Risk Identification, Probability, and Mitigation

Table 8.2:  Risk Register

| Risk ID | Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R-001 | EVV aggregator API credentials and account access not confirmed before Milestone 2 | High | High | Deliver full integration design and data-field mapping documentation regardless of live access. Maintain a mock aggregator endpoint for development and testing. Track as at-risk dependency with weekly status updates to project lead. |
| R-002 | AWS Bedrock and Claude model access not provisioned by Team A before Milestone 2 development begins | Medium | High | Complete invoicing migration scope documentation and prompt design in Milestone 2. Defer implementation to Milestone 3 if access is unavailable. Coordinate provisioning timeline with Team A at weekly sync. |
| R-003 | PHI or sensitive data leaked via Bedrock prompt construction or AI output | Low | Critical | Apply pre-prompt redaction for all PHI/PII fields. Operate Bedrock only under BAA-covered AWS configuration. Enforce output schema validation and require human reviewer approval before any AI-extracted value is saved. |
| R-004 | Wearable API rate limits, consent requirements, or sandbox restrictions block integration testing | Medium | Medium | Use Fitbit developer sandbox, Apple HealthKit simulator, and Google Health Connect test environment. Design integration layer to degrade gracefully when provider data is unavailable. Document any untestable paths clearly. |
| R-005 | Invite token replay or unauthorized care-circle access due to token handling vulnerabilities | Low | High | Generate cryptographically signed JWT tokens with ≤72-hour TTL and single-use enforcement. Log all token validation events. Reject expired or already-used tokens with deterministic error messaging. |
| R-006 | Scope creep from client-directed additions to digitized form list or assessment fields | Medium | Medium | Freeze form scope at Milestone 1 gap review with client sign-off. Document any additions as change requests and evaluate impact on timeline and budget before acceptance. |
| R-007 | Team member availability reduced by academic or personal obligations during peak delivery weeks | Medium | Medium | Distribute critical path tasks across at least two team members. Identify backup owners for each feature area. Track sprint capacity weekly and escalate to project lead if bandwidth drops below threshold. |
| R-008 | Merge conflicts or integration failures with shared CareConnect codebase owned by other teams | Medium | Medium | Develop all Team D features in the designated Team D branch. Follow the weekly integration schedule with peer-reviewed pull requests. Resolve conflicts before merge and coordinate with Team A on shared infrastructure touchpoints. |

Note. Risk IDs are unique and permanent. Probability and Impact are rated Low, Medium, High, or Critical. Risks are reviewed at each sprint review and escalated to the project lead when status changes.

## 8.3 Risk and Budget Alignment

The risks above connect directly to budget and schedule. Where a risk increases estimated effort, the corresponding WBS task and budget line should be re-evaluated through the change management process.

Table 8.3 Risk and Budget Assessment

| Risk | Budget / EVM Impact |
| --- | --- |
| R-001: EVV aggregator delayed | May increase Technical Architect / DevOps hours for integration design documentation |
| R-002: Bedrock access delayed | May defer Software Developer hours from Milestone 2 to Milestone 3; no cost increase if scope is unchanged |
| R-004: Wearable API limits | May increase QA / Tester hours for fallback path testing and graceful-degradation validation |
| R-006: Scope creep | Any client-directed additions must follow change management and will increase Business Analyst and Developer hours |
| R-007: Team availability | Reduced capacity increases schedule risk; may require re-sequencing WBS tasks across milestones |

Note. Any risk that materially increases effort must be documented as a change request and reflected in the WBS, budget, and EVM table.

# 9. Budget Estimate

The budget estimate below is built from the Team D Work Breakdown Structure. Each WBS task is assigned to the standard BLS-based labor category that best matches the work, and cost is calculated using the class-standard hourly rates. Infrastructure costs reflect the three-month MVP delivery window.

## 9.1 Labor Cost Estimate

Table 9.1:  WBS Labor Cost Estimate

| # | Task / Work Package | Budget Role Category | Milestone | Est. Hours | Hourly Rate | Est. Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | EVV gap analysis and current-state workflow review | Business Analyst / Requirements Analyst | M1 | 12 | $49/hr | $588 |
| 2 | EVV aggregator dependency tracking — dashboard widget | Software Developer / Programmer | M2 | 16 | $64/hr | $1,024 |
| 3 | EVV enhancement implementation (gap-review findings) | Software Developer / Programmer | M3 | 24 | $64/hr | $1,536 |
| 4 | EVV integration design documentation | Technical Writer / Documentation Specialist | M2 | 10 | $44/hr | $440 |
| 5 | EVV feature testing and regression validation | QA / Tester / Accessibility Tester | M3 | 12 | $49/hr | $588 |
| 6 | Invoice service architecture — Bedrock migration design | Technical Architect / DevOps / Cloud Architect | M2 | 10 | $63/hr | $630 |
| 7 | Bedrock/Claude migration implementation | Software Developer / Programmer | M3 | 28 | $64/hr | $1,792 |
| 8 | Invoice extraction accuracy validation and prompt design | Software Developer / Programmer | M3 | 12 | $64/hr | $768 |
| 9 | Invoice reviewer workflow — continuity verification | QA / Tester / Accessibility Tester | M3 | 10 | $49/hr | $490 |
| 10 | Bedrock migration technical documentation | Technical Writer / Documentation Specialist | M4 | 8 | $44/hr | $352 |
| 11 | QR and invite-link onboarding requirements and flow design | Business Analyst / Requirements Analyst | M1 | 10 | $49/hr | $490 |
| 12 | QR/invite UI design and screen flow | UI/UX Designer | M2 | 10 | $47/hr | $470 |
| 13 | Token issuance, delivery, and lifecycle implementation | Software Developer / Programmer | M3 | 20 | $64/hr | $1,280 |
| 14 | Invite acceptance, role assignment, and error handling | Software Developer / Programmer | M3 | 16 | $64/hr | $1,024 |
| 15 | QR/invite onboarding testing | QA / Tester / Accessibility Tester | M3 | 8 | $49/hr | $392 |
| 16 | Wearable integration architecture and OAuth design | Technical Architect / DevOps / Cloud Architect | M2 | 10 | $63/hr | $630 |
| 17 | Wearable device connector implementation (Fitbit, HealthKit, Health Connect) | Software Developer / Programmer | M3 | 32 | $64/hr | $2,048 |
| 18 | Threshold alert rules and notification integration | Software Developer / Programmer | M3 | 12 | $64/hr | $768 |
| 19 | Wearable dashboard UI — sync status display | UI/UX Designer | M3 | 8 | $47/hr | $376 |
| 20 | Wearable integration testing and stale-sync validation | QA / Tester / Accessibility Tester | M3 | 10 | $49/hr | $490 |
| 21 | Wearable integration documentation | Technical Writer / Documentation Specialist | M4 | 6 | $44/hr | $264 |
| 22 | Home care form analysis and prioritization | Business Analyst / Requirements Analyst | M1 | 8 | $49/hr | $392 |
| 23 | Digital form UI design (W-4, I-9, Direct Deposit) | UI/UX Designer | M2 | 12 | $47/hr | $564 |
| 24 | Digital form implementation and field validation | Software Developer / Programmer | M3 | 24 | $64/hr | $1,536 |
| 25 | Document status lifecycle and admin review interface | Software Developer / Programmer | M3 | 16 | $64/hr | $1,024 |
| 26 | Document digitization testing | QA / Tester / Accessibility Tester | M3 | 10 | $49/hr | $490 |
| 27 | Screening assessment requirements and field specification | Business Analyst / Requirements Analyst | M1 | 8 | $49/hr | $392 |
| 28 | Screening form UI design | UI/UX Designer | M2 | 8 | $47/hr | $376 |
| 29 | Screening form implementation | Software Developer / Programmer | M3 | 16 | $64/hr | $1,024 |
| 30 | Screening assessment testing | QA / Tester / Accessibility Tester | M3 | 6 | $49/hr | $294 |
| 31 | Comprehensive assessment requirements and field specification | Business Analyst / Requirements Analyst | M1 | 8 | $49/hr | $392 |
| 32 | Comprehensive assessment form UI design | UI/UX Designer | M2 | 8 | $47/hr | $376 |
| 33 | Comprehensive assessment implementation | Software Developer / Programmer | M3 | 20 | $64/hr | $1,280 |
| 34 | Comprehensive assessment testing | QA / Tester / Accessibility Tester | M4 | 8 | $49/hr | $392 |
| 35 | Project Plan drafting and milestone documentation | Technical Writer / Documentation Specialist | M1 | 16 | $44/hr | $704 |
| 36 | SRS drafting | Technical Writer / Documentation Specialist | M1 | 14 | $44/hr | $616 |
| 37 | Technical Design Document | Technical Writer / Documentation Specialist | M2 | 14 | $44/hr | $616 |
| 38 | Software Test Plan | Technical Writer / Documentation Specialist | M2 | 10 | $44/hr | $440 |
| 39 | Programmer Guide and Deployment Guide | Technical Writer / Documentation Specialist | M3 | 14 | $44/hr | $616 |
| 40 | User Guide and Test Report | Technical Writer / Documentation Specialist | M4 | 12 | $44/hr | $528 |
| 41 | Sprint coordination, EVM tracking, and milestone management | Project Manager / Team Lead | All | 30 | $48/hr | $1,440 |
| 42 | Risk tracking and stakeholder communication | Project Manager / Team Lead | All | 10 | $48/hr | $480 |
| TOTAL |  |  |  | 556 |  | $30,412 |

Note. Estimated Cost = Estimated Hours × Standard Hourly Rate. Rates are based on U.S. Bureau of Labor Statistics Occupational Outlook Handbook median annual wages converted at 2,080 hours per year (40 hours/week × 52 weeks).

## 9.2 Budget Summary by Role

Table 9.2:  Budget Summary by Role Category

| Budget Role Category | Hourly Rate | Estimated Hours | Estimated Cost |
| --- | --- | --- | --- |
| Project Manager / Team Lead | $48/hr | 40 | $1,920 |
| Business Analyst / Requirements Analyst | $49/hr | 46 | $2,254 |
| UI/UX Designer | $47/hr | 46 | $2,162 |
| Technical Architect / DevOps / Cloud Architect | $63/hr | 20 | $1,260 |
| Software Developer / Programmer | $64/hr | 236 | $15,104 |
| QA / Tester / Accessibility Tester | $49/hr | 64 | $3,136 |
| Technical Writer / Documentation Specialist | $44/hr | 104 | $4,576 |
| Total |  | 556 | $30,412 |

Note. Hours are distributed across Milestones 1–4. The highest-effort category is Software Developer / Programmer, reflecting the feature-implementation depth of Team D's assigned scope.

## 9.3 Infrastructure Cost

### 9.3.1 Core Services

Table 9.3.1:  Infrastructure Cost Estimate

| Service | Usage | Unit Cost | Monthly Cost |
| --- | --- | --- | --- |
| AWS Lambda + API Gateway | Serverless compute and REST/WebSocket routing at pilot scale | $10 | $10 |
| Amazon RDS for PostgreSQL | Single-AZ managed relational database with automated backups | $60 | $60 |
| Amazon S3 | Object storage for uploads, exports, recordings, and OCR artifacts | $8 | $8 |
| AWS CloudWatch | Logs, metrics, alarms, and operational dashboards | $15 | $15 |
| AWS KMS + Secrets Manager | Encryption key management and secure credential storage | $6 | $6 |
| AWS Bedrock (Claude) | AI inference for invoice extraction and related workflows | $45 | $45 |
| AWS Chime SDK | Audio/video calling, recording, and transcription services | $65 | $65 |
| SendGrid / AWS SES | Transactional email delivery | $15 | $15 |
| Firebase Cloud Messaging | Mobile push notification delivery (pilot volume) | $0 | $0 |
| Contingency reserve (15%) | Reserve for usage spikes and testing overrun | $34 | $34 |
| Total Monthly |  |  | $258 |

## 9.4 Total Budget Summary

Table 9.4:  Budget Summary

| Category | Estimated Cost (USD) |
| --- | --- |
| Labor (full project scope, all milestones) | $30,412 |
| Infrastructure (3-month MVP period) | $774 |
| Third-Party / One-Time Fees | Variable — excluded from fixed estimate |
| Total Estimated Project Budget | $31,186 |

Note. Labor cost is based on estimated hours × BLS standard hourly rates and covers the full capstone scope across all four milestones. Infrastructure cost covers three months of AWS pilot-scale operations. Total budget reflects Team D's assigned scope only.

## 9.5 EVM Tracking Table

The EVM table below tracks planned versus actual progress for each WBS task area. Task Budget = Planned Hours × Standard Hourly Rate. Actual Cost = Actual Hours × Standard Hourly Rate. Earned Value = Task Budget × Percent Complete. Status is Green (on track), Yellow (minor variance), or Red (significant risk).

Table 9.5:  EVM Tracking Snapshot

| Task Area | Role Categories | Planned Hrs | Actual Hrs | % Done | Planned Value | Earned Value | Actual Cost | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EVV Enhancements | BA/DEV/QA/TW | 74 | 0 | 0% | $4,070 | $0 | $0 | Green |
| AI-Assisted Invoicing (Bedrock) | ARCH/DEV/QA/TW | 68 | 0 | 0% | $3,740 | $0 | $0 | Green |
| QR/Invite Onboarding | BA/UX/DEV/QA | 64 | 0 | 0% | $3,520 | $0 | $0 | Green |
| Wearable Device Integration | ARCH/DEV/UX/QA/TW | 78 | 0 | 0% | $4,290 | $0 | $0 | Green |
| Home Care Document Digitization | BA/UX/DEV/QA | 70 | 0 | 0% | $3,850 | $0 | $0 | Green |
| Screening & Comprehensive Assessment | BA/UX/DEV/QA | 82 | 0 | 0% | $4,510 | $0 | $0 | Green |
| Documentation | TW | 80 | 0 | 0% | $4,400 | $0 | $0 | Green |
| Project Management | PM | 40 | 0 | 0% | $2,200 | $0 | $0 | Green |

Note. EVM table is updated weekly during sprint reviews. Planned Value and Earned Value use a blended rate approximation for summary reporting; exact task-level costs are tracked in the WBS labor table above. Actual Hours and Percent Complete are updated as milestones are completed.

# 10. Roles & Responsibilities

## 10.1 Roles

Table 10.1: Team Roles and Responsibilities

| Name | Role | Responsibilities |
| --- | --- | --- |
| Joriel Rivas | Class Project Manger | Organize team project progress for all teams, provide updates to course professor |
| Davon Davis | Team Lead | Organize team project deliverable, Provide project progress to Class Project Manager |
| Requirement Business Analyst | Chris | Clarify user roles/workflows, Define what features are in/out of scope, Maintain glossary/terminology consistency |
| Angel | Frontend | UI implementation, QR workflows, form digitization interfaces |
| Nhial | Backend | API development, Bedrock integration, EVV services, database support |
| Bernabe | QA / Security | Testing workflows, regression testing, defect verification |

Note. Add rows for each team member.

## 10.2 RACI Matrix

| Task / Activity | Team Lead | Business Analyst | Frontend | Backend | QA/ Security |
| --- | --- | --- | --- | --- | --- |
| Project Planning | A/R | C | C | I | C |
| Requirements Gathering | A | C | C | I | R |
| EVV Enhancements | A | R | R | C | I |
| Invoice Workflow | A | C | R | C | I |
| QR/Invite Workflow | A | R | C | C | I |
| Wearable Integration | A | C | R | C | I |
| Testing & QA | A | C | C | R | I |
| Documentation | A | I | I | I | R |

Note. R = Responsible, A = Accountable, C = Consulted, I = Informed.

# 11. Monitoring and Reporting

## 11.1 Objectives

Project monitoring and reporting ensure visibility into sprint progress, feature completion, blockers, testing status, and overall milestone readiness throughout the capstone lifecycle.

## 11.2 Intra-Team Monitoring and Reporting

The following practices govern how Team D monitors progress and maintain visibility into sprint health, task completion, and overall milestone readiness. These mechanisms operate on a continuous basis throughout the capstone and are designed to surface blockers early, ensure accountability across the team, and keep all members aligned on delivery status.

- Weekly Sprint Reviews - The team will conduct weekly sprint review meetings to discuss completed work, blockers, upcoming priorities, and milestone progress.

- Task Tracking - GitHub Projects or equivalent tracking tools will be used to monitor assigned tasks, progress status, and sprint workload.

- Code Reviews and CI/CD Checks - Pull requests will require peer review before merging. Build validation and automated checks will be monitored regularly.

- Documentation Tracking - Deliverables and project documentation will be updated continuously to ensure milestone readiness.

## 11.3 Project Communications

### 11.3.1 Internal Meetings

The following recurring internal meetings support sprint execution, backlog management, and day-to-day coordination among team members.

- Weekly team meetings via Microsoft Teams

- Sprint planning and backlog refinement sessions

- Ad-hoc technical discussions as needed

### 11.3.2 Internal-External Meetings

The following meetings connect Team D with external stakeholders, including the faculty advisor and client, to ensure alignment, gather feedback, and address clarifications as they arise.

- Meetings with Professor Assadullah for milestone reviews and project feedback

- Client/stakeholder clarification discussions when required

### 11.3.3 Cross-Team Meetings

Cross-team meetings will be conducted as needed to coordinate dependencies between Team D and other CareConnect capstone teams. These meetings will focus on shared functionality, integration points, infrastructure dependencies, and project-wide deliverables that require collaboration across teams. Examples include coordination with Team A regarding AWS infrastructure, deployment, and RBAC configuration; discussions with Team B regarding accessibility considerations; and coordination with other feature teams when shared APIs, workflows, or data models are affected. All action items, decisions, risks, and dependency updates resulting from cross-team meetings will be documented in meeting notes and tracked through GitHub Issues, project boards, or the team’s decision log. Progress on cross-team dependencies will be reviewed during weekly sprint reviews to ensure blockers are identified early and communicated to the appropriate stakeholders.

## 11.4 Quality Plan

The project will use peer reviews, testing validation, documentation reviews, and sprint retrospectives to maintain quality standards. Testing progress and unresolved defects will be tracked throughout development.

# 12. Assumptions

The following assumptions underpin the project plan and schedule. Each assumption carries a validation status indicating whether it has been confirmed, is currently under review, or represents an active risk to the project. Changes to any of these assumptions must be assessed for impact on scope, timeline, and budget through the change management process.

- Existing CareConnect infrastructure and repositories will remain accessible throughout development. Status: Validated.

- Team members will have access to required development tools and collaboration platforms. Status: Validated.

- AWS Bedrock and Claude integration services will remain available for testing and prototyping. Status: Under Review.

- Wearable APIs and integrations will provide accessible developer documentation and test environments. Status: Under Review.

- EVV aggregator access or documentation will be obtainable within the project timeline. Status: At Risk.

- Home care forms selected for digitization are approved for academic implementation. Status: Validated.

- Team members will contribute consistently throughout the capstone timeline. Status: Under Review.

# 13. Constraints

The following constraints define the boundaries within which the project must operate. Unlike assumptions, constraints are fixed conditions that cannot be changed by the team and must be planned around the outset. Any constraint that materially affects scope or schedule should be surfaced through the change management process.

- The project must be completed within the SWEN 670 capstone timeline.

- Team members are balancing coursework and external responsibilities.

- Some third-party integrations may require external approvals or access.

- Healthcare compliance considerations may limit implementation scope.

- AI-assisted workflows must remain within academic and ethical boundaries.

- Wearable device support may vary depending on available APIs and testing access.

- Scope changes may impact delivery timelines if not managed properly.

# 14. Work Breakdown Structure (WBS)

The Team D WBS is organized by feature area and decomposed into work packages aligned to milestone deliverables. Each work package is assigned to a single budget role category, carries an estimated hour commitment, and maps to at least one milestone. The WBS drives the budget in Section 9 and the EVM tracking table. Any approved scope change must be reflected in the WBS, budget summary, EVM table, schedule, and risks.

Table 14:  Work Breakdown Structure

| WBS ID | Task / Work Package | Budget Role Category | Milestone | Est. Hours | Rate | Est. Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Electronic Visit Verification (EVV) |  |  |  |  |  |  |
| 1.1 | EVV gap analysis and current-state workflow review | Business Analyst / Requirements Analyst | M1 | 12 | $49/hr | $588 |
| 1.2 | EVV aggregator dependency tracking — admin dashboard widget | Software Developer / Programmer | M2 | 16 | $64/hr | $1,024 |
| 1.3 | EVV enhancement implementation (gap-review findings) | Software Developer / Programmer | M3 | 24 | $64/hr | $1,536 |
| 1.4 | EVV integration design documentation (field mapping, error handling) | Technical Writer / Documentation Specialist | M2 | 10 | $44/hr | $440 |
| 1.5 | EVV feature testing and regression validation | QA / Tester / Accessibility Tester | M3 | 12 | $49/hr | $588 |
| 2. AI-Assisted Invoicing — Bedrock/Claude Migration |  |  |  |  |  |  |
| 2.1 | Invoice service architecture — Bedrock migration design | Technical Architect / DevOps / Cloud Architect | M2 | 10 | $63/hr | $630 |
| 2.2 | Bedrock/Claude migration implementation | Software Developer / Programmer | M3 | 28 | $64/hr | $1,792 |
| 2.3 | Invoice extraction accuracy validation and prompt design | Software Developer / Programmer | M3 | 12 | $64/hr | $768 |
| 2.4 | Invoice reviewer workflow — continuity and regression verification | QA / Tester / Accessibility Tester | M3 | 10 | $49/hr | $490 |
| 2.5 | Bedrock migration technical documentation | Technical Writer / Documentation Specialist | M4 | 8 | $44/hr | $352 |
| 3. QR Code and Invite-Link Onboarding |  |  |  |  |  |  |
| 3.1 | QR and invite-link requirements and invitation lifecycle design | Business Analyst / Requirements Analyst | M1 | 10 | $49/hr | $490 |
| 3.2 | QR/invite UI design and confirmation screen flow | UI/UX Designer | M2 | 10 | $47/hr | $470 |
| 3.3 | Token issuance, delivery (URL + QR), and lifecycle implementation | Software Developer / Programmer | M3 | 20 | $64/hr | $1,280 |
| 3.4 | Invite acceptance, role assignment, and error handling | Software Developer / Programmer | M3 | 16 | $64/hr | $1,024 |
| 3.5 | QR/invite onboarding testing — expiry, replay, role assignment | QA / Tester / Accessibility Tester | M3 | 8 | $49/hr | $392 |
| 4. Wearable Device Integration |  |  |  |  |  |  |
| 4.1 | Wearable integration architecture and OAuth flow design | Technical Architect / DevOps / Cloud Architect | M2 | 10 | $63/hr | $630 |
| 4.2 | Device connector implementation (Fitbit, Apple HealthKit, Google Health Connect) | Software Developer / Programmer | M3 | 32 | $64/hr | $2,048 |
| 4.3 | Threshold alert rules and caregiver notification integration | Software Developer / Programmer | M3 | 12 | $64/hr | $768 |
| 4.4 | Wearable dashboard UI — metric display and sync-status indicators | UI/UX Designer | M3 | 8 | $47/hr | $376 |
| 4.5 | Wearable integration and stale-sync alert testing | QA / Tester / Accessibility Tester | M3 | 10 | $49/hr | $490 |
| 4.6 | Wearable integration documentation | Technical Writer / Documentation Specialist | M4 | 6 | $44/hr | $264 |
| 5. Home Care Document Digitization |  |  |  |  |  |  |
| 5.1 | Home care form analysis and digitization prioritization | Business Analyst / Requirements Analyst | M1 | 8 | $49/hr | $392 |
| 5.2 | Digital form UI design (W-4, I-9, Direct Deposit Authorization) | UI/UX Designer | M2 | 12 | $47/hr | $564 |
| 5.3 | Digital form implementation and field-level validation | Software Developer / Programmer | M3 | 24 | $64/hr | $1,536 |
| 5.4 | Document status lifecycle and admin review interface | Software Developer / Programmer | M3 | 16 | $64/hr | $1,024 |
| 5.5 | Document digitization testing — validation, status, admin workflow | QA / Tester / Accessibility Tester | M3 | 10 | $49/hr | $490 |
| 6. Screening and Comprehensive Assessment |  |  |  |  |  |  |
| 6.1 | Screening assessment requirements and field specification | Business Analyst / Requirements Analyst | M1 | 8 | $49/hr | $392 |
| 6.2 | Comprehensive assessment requirements and field specification | Business Analyst / Requirements Analyst | M1 | 8 | $49/hr | $392 |
| 6.3 | Screening form UI design | UI/UX Designer | M2 | 8 | $47/hr | $376 |
| 6.4 | Comprehensive assessment form UI design | UI/UX Designer | M2 | 8 | $47/hr | $376 |
| 6.5 | Screening form implementation | Software Developer / Programmer | M3 | 16 | $64/hr | $1,024 |
| 6.6 | Comprehensive assessment implementation | Software Developer / Programmer | M3 | 20 | $64/hr | $1,280 |
| 6.7 | Screening assessment testing | QA / Tester / Accessibility Tester | M3 | 6 | $49/hr | $294 |
| 6.8 | Comprehensive assessment testing | QA / Tester / Accessibility Tester | M4 | 8 | $49/hr | $392 |
| 7. Documentation |  |  |  |  |  |  |
| 7.1 | Project Plan drafting and milestone documentation | Technical Writer / Documentation Specialist | M1 | 16 | $44/hr | $704 |
| 7.2 | Software Requirements Specification (SRS) | Technical Writer / Documentation Specialist | M1 | 14 | $44/hr | $616 |
| 7.3 | Technical Design Document | Technical Writer / Documentation Specialist | M2 | 14 | $44/hr | $616 |
| 7.4 | Software Test Plan | Technical Writer / Documentation Specialist | M2 | 10 | $44/hr | $440 |
| 7.5 | Programmer Guide and Deployment and Operations Guide | Technical Writer / Documentation Specialist | M3 | 14 | $44/hr | $616 |
| 7.6 | User Guide and Test Report | Technical Writer / Documentation Specialist | M4 | 12 | $44/hr | $528 |
| 8. Project Management |  |  |  |  |  |  |
| 8.1 | Sprint coordination, EVM tracking, and milestone management | Project Manager / Team Lead | All | 30 | $48/hr | $1,440 |
| 8.2 | Risk tracking and stakeholder communication | Project Manager / Team Lead | All | 10 | $48/hr | $480 |
|  | TOTAL |  |  | 556 |  | $30,412 |

Note. Total estimated labor: 556 hours / $30,412. Estimated Cost = Estimated Hours × Standard Hourly Rate (BLS-based). Hours are estimates and will be updated through EVM tracking as the project progresses.

## 14.2 WBS Hierarchy

The WBS is organized across four levels:

• Level 1 — Team D Feature Program

• Level 2 — Feature Epics: EVV, AI Invoicing, QR/Invite, Wearables, Document Digitization, Assessment Workflows, Documentation, Project Management

• Level 3 — Work Packages (rows in the WBS table above), each assigned to one role category and one or more milestones

• Level 4 — Implementation and validation tasks tracked in GitHub Issues and the sprint backlog

The WBS table is the authoritative source for budget and EVM. Any approved change to scope must be reflected in this table, the budget summary in Section 9, and the EVM tracking table before the next milestone submission.

# 15. Change Management Procedures

All requested project changes must be documented, reviewed, and approved before implementation. Change requests may originate from team members, faculty, or project stakeholders.

The following process will be used:

- A proposed change will be documented with a description, rationale, and potential impact.

- The team will evaluate the impact on scope, timeline, dependencies, and workload.

- The Project Lead will coordinate review discussions with the team and stakeholders.

- Approved changes will be added to the sprint backlog and project documentation.

- Rejected or deferred changes will be documented for future consideration.

Minor task adjustments may be handled during sprint planning, while major scope changes require team-wide review and stakeholder communication to avoid project disruption.

## 15.1 Initiation

Any team member, stakeholder, client representative, or faculty advisor may propose a project change. Changes may include:

- Functional requirement updates

- Scope modifications

- Architecture or infrastructure adjustments

- Timeline or milestone changes

- Security or compliance updates

- API or integration modifications

- Documentation corrections or clarifications

All proposed changes must be documented in a shared project tracking system such as GitHub Issues, Microsoft Teams, or the shared project documentation repository. Each request must include:

- Description of the proposed change

- Reason for the change

- Impacted system areas or deliverables

- Estimated implementation effort

- Potential risks or dependencies

- Requested priority level

## 15.2 Review

Table 15.2: Change Control Board Members

| CCB Member | Role | Responsibilities |
| --- | --- | --- |
| Dr. Assadullah Roy Gordon | Course Instructor / Client Client | Final approval or rejection |
| Joriel Rivas Davon Davis | Project Manager Team Lead | Triage and prioritization |
| CareConnect Team Members | BA, Developers, Testers | Impact analysis and effort estimates. Technical feasibility assessment. |

## 15.3 Authorization and Implementation

Approved changes will be prioritized and scheduled according to project timelines and sprint capacity. Once approved:

- Related documentation must be updated

- Impacted requirements must be revised

- Development tasks will be assigned

- Testing requirements will be adjusted as necessary

- Stakeholders will be notified of the approved modification

Rejected changes will remain documented for future reference but will not be implemented during the current milestone unless reconsidered through a future review cycle.

All implemented changes must be reflected in:

- Project Plan updates

- SRS revisions

- Technical Design Documents

- Test Plans

- Deployment or Programmer Guides where applicable

## 15.4 Version Control and Traceability

GitHub will serve as the primary version control platform for application code and related technical artifacts. Documentation revisions will be tracked using version history tables and document revision notes.

All major project changes must maintain traceability between:

- Requirements

- Design decisions

- Implementation tasks

- Testing artifacts

- Final deliverables

Pull requests, issue tracking, and commit history will be used to maintain visibility into when changes were introduced and who approved them.

## 15.5 Emergency or Critical Changes

Critical issues affecting system security, data integrity, application stability, or milestone deliverability may require expedited changes outside the standard review cycle. These changes may be approved directly by the Team Lead and Technical Lead with immediate notification provided to affected stakeholders.

Emergency changes must still:

- Be documented

- Undergo testing when possible

- Be included in subsequent project documentation updates

- Be reviewed retrospectively during sprint review meetings

# 16. Appendices

## 16.1 Glossary of Terms

Table 16.1:  Glossary of Terms

| Term | Definition |
| --- | --- |
| Agile-Scrum | A hybrid project management methodology combining Agile principles with Scrum ceremonies such as sprint planning, daily standups, sprint reviews, and retrospectives. Used by Team D for iterative delivery. |
| Aggregator | A third-party system responsible for routing Electronic Visit Verification records from home care agencies to state Medicaid programs. Team D tracks this as an external project dependency. |
| Care Circle | A group within CareConnect that connects a patient with their assigned caregivers and authorized family members, enabling coordinated healthcare management. |
| CareConnect | The healthcare coordination platform extended by Team D. It supports caregiver workflows, patient onboarding, wearable device integration, invoicing, and Electronic Visit Verification. |
| Caregiver | An individual responsible for providing home care services to a patient. Caregivers use CareConnect to manage visit records, submit invoices, and coordinate with care circle members. |
| Change Request | A formal document submitted to propose a modification to project scope, timeline, or deliverables. All change requests are reviewed and approved by the Change Control Board before implementation. |
| Deliverable | A tangible output produced as part of the project, such as the Project Plan, Software Requirements Specification, or Technical Design Document. |
| Document Digitization | The process of converting paper-based home care forms (e.g., tax withholding, employment eligibility, health assessments) into structured digital forms within CareConnect. |
| EDI | Electronic Data Interchange. A standardized format used to export visit records from the EVV module for submission to state Medicaid payers. |
| Invoice Extraction | An AI-assisted workflow that automatically extracts key fields (vendor name, date, invoice number, line items, totals) from uploaded invoice images using AWS Bedrock with Claude. |
| Milestone | A defined project checkpoint with associated deliverables and a due date. Team D has four milestones spanning May through August 2026. |
| Onboarding | The process of adding a new user (caregiver or family member) to a CareConnect care circle using a QR code or secure invite link. |
| Sprint | A time-boxed iteration, typically one to two weeks, during which the team completes a set of planned tasks. Sprints are the core delivery unit of the Agile-Scrum methodology. |
| Stakeholder | Any individual or organization with an interest in the project outcome, including the client, faculty mentor, team members, caregivers, patients, and third-party platform providers. |
| Wearable Device Integration | The connection between CareConnect and external device platforms (Fitbit, Apple HealthKit, Google Health Connect) to collect and display patient health metrics such as heart rate and step count. |

Table 16.2:  Acronyms

| Acronym | Definition |
| --- | --- |
| AI | Artificial Intelligence |
| API | Application Programming Interface |
| AWS | Amazon Web Services |
| BA | Business Analyst |
| CCB | Change Control Board |
| CI/CD | Continuous Integration / Continuous Delivery |
| CORS | Cross-Origin Resource Sharing |
| EDI | Electronic Data Interchange |
| EVV | Electronic Visit Verification |
| FHIR | Fast Healthcare Interoperability Resources |
| HIPAA | Health Insurance Portability and Accountability Act |
| HTTPS | Hypertext Transfer Protocol Secure |
| JPA | Java Persistence API |
| JWT | JSON Web Token |
| KMS | Key Management Service |
| MVP | Minimum Viable Product |
| OCR | Optical Character Recognition |
| PMP | Project Management Plan |
| QA | Quality Assurance |
| QR | Quick Response (code) |
| RACI | Responsible, Accountable, Consulted, Informed |
| RBAC | Role-Based Access Control |
| RDS | Relational Database Service |
| REST | Representational State Transfer |
| SDK | Software Development Kit |
| SRS | Software Requirements Specification |
| TBD | To Be Determined |
| UI | User Interface |
| URL | Uniform Resource Locator |
| USD | United States Dollar |
| USPS | United States Postal Service |
| UX | User Experience |
| VPAT | Voluntary Product Accessibility Template |
| WAF | Web Application Firewall |
| WBS | Work Breakdown Structure |

## 16.2 References

U.S. Bureau of Labor Statistics. (2025). Project management specialists. Occupational Outlook Handbook. https://www.bls.gov/ooh/business-and-financial/project-management-specialists.htm

U.S. Bureau of Labor Statistics. (2025). Management analysts. Occupational Outlook Handbook. https://www.bls.gov/ooh/business-and-financial/management-analysts.htm

U.S. Bureau of Labor Statistics. (2025). Web developers and digital designers. Occupational Outlook Handbook. https://www.bls.gov/ooh/computer-and-information-technology/web-developers.htm

U.S. Bureau of Labor Statistics. (2025). Computer network architects. Occupational Outlook Handbook. https://www.bls.gov/ooh/computer-and-information-technology/computer-network-architects.htm

U.S. Bureau of Labor Statistics. (2025). Software developers, quality assurance analysts, and testers. Occupational Outlook Handbook. https://www.bls.gov/ooh/computer-and-information-technology/software-developers.htm

U.S. Bureau of Labor Statistics. (2025). Technical writers. Occupational Outlook Handbook. https://www.bls.gov/ooh/media-and-communication/technical-writers.htm